## Sheet1
GOAL | IMPORTANCE | ACTIONS NEEDED | TIME REQUIRED | MILESTONE | RESOURCES NEEDED | SKILLS TO BE LEARNT
Develop a car density etimation technology using SAR | As a long-term goal, Our objective is to detect changes in our environment using SAR imagery. As a short term goal, we limit our environment to parking lots and want to monitor chnages in car count over time. Car count is an index of the area economic activity. Monitoring changes in car count (or density) can reveal useful insight about the changes in economics/revenue of that area. | 1. Conduct literature survey on Car-density estimation and related problems and summarize the key arguments | 4 weeks (3 week for paper reading and 1 week for report) | read ~50 research papers and report on the key arguments/methods |  |  | S: specific
|  | 2. Find the problems in the current methods and select one problem | 1 week | List of all problems with the most important one |  |  | M: measurable
|  | 3. Select a baseline method which has the problem and implement it | 1 week | Block diagram of baseline and quantitative result |  |  | A: Achievable
|  | 4. Re-analyze the problem and think ways to solve it | 2 weeks | vizualization of the problem and conditions of occurence, list of ways to solve it |  |  | R: Relevant
|  | 5. Propose a new method and implement it. Show the improvement quantitatively. | 1~2 weeks | Block diagram of propsed method, quantitative result and %improvement |  |  | T: Time-bound
|  | 6. Test the method for different cases and find loopholes | 2 weeks | List of success and failure cases (conditions and %difference)