## Sheet1
Priority No. | Tasks | Sub-tasks | Deadline | F | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su
1 | Multitask TR |  | 2019-11-26 | 8 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Collect Results | bar: F 8 to Th 21
Write Content | bar: F 22 to Su 24
Edit | bar: M 25
Submit | bar: T 26
2 | IGARSS Paper |  | 2019-12-20
Make 1st Draft | bar: W 27 to Th 28
Set approval meeting | bar: F 29
Edit Paper | bar: F 29 to S 30
Submit | bar: F 20
3 | Organize Code |  | 2019-12-05
Delete unnecessary code and results | bar: Su 1 to M 2
Document and clean each code | bar: T 3 to W 4
Write README | bar: Th 5
5 | Research proposal for SAR-Optical |  | 2019-12-10
Learn how to write proposal | bar: W 20 to S 30
Read some papers for lit survey | bar: Su 1 to Th 5
Make proposal | bar: F 6 to Su 8
Discuss with team and revise | bar: M 9 to W 11
Submit | bar: Th 12
4 | AS-2 Feasibility study TR |  | 2019-12-17
Collect Results | bar: Th 12 to F 13
Make TR using PPT | bar: S 14
Show to team and discuss | bar: Su 15 to M 16
Submit | bar: T 17
6 | Exit Process |  | 2019-12-24
Notification | bar: S 23
Book Tickets | bar: W 27
Start Paper Work and selling items | bar: W 27 to Su 1
Collect important stuff | bar: T 17 to Th 19
Delete useless things and organize | bar: Th 19 to Su 22